| DOMAIN: ECONOMIC STABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PRIORITY AREA: NUTRITION SECURITY |  |  |  |  |  |  |  |
| GOAL: Increase Food Security OBJECTIVE 3.1: By December 31, 2030, increase food security among adults who make less than $25,000 by 5% from 78% to 81.9%. (Data Source: Orange County Community Health Survey, 2024) DISPARITIYADDRESSED: Individuals with low social-economic status (SES) |  |  |  |  |  |  |  |
| Evidence-Based Strategy | Lead Partners |  | Timeframe |  | Evaluation Measure |  | Outcome: Product/Result |
| Conduct standardized screening of unmet nutritional security needs and provide referrals to state, local, and federal benefit programs and community-based health-related social needs providers to address unmet needs | Staff Time: OCDOH, Bon Secours Community Hospital (BSCH), Garnet Health, St. Anthony Community Hospital (SACH), Orange County Food Security and Healthy Eating Workgroup Advisory Partners: OC CHIP Steering Committee, CCE, Cornerstone, SUNY Orange, Orange County Office for the Aging (OFA), Orange County Department of Social Services (DSS), Sun River Health, Head Start, Enlarged City of Newburgh School District, United Way of Orange County, local food pantries, Wellness Inspiring Spiritual Health |  | July 1, 2026 through December 31, 2030 |  | # of community-based organizations (CBOs) conducting screenings and facilitation of referrals to benefit programs |  | Increased number of food insecure residents connected to resources |
| PERFORMANCE MEASURES |  |  |  |  |  |  |  |
| Short Term Process Indicators for Objective 3.1 |  | Baseline |  | Source |  | Frequency |  |
| By December 31, 2026, establish a baseline of CBOs currently screening for food security with the OC Food Security and Healthy Eating Workgroup. |  | None |  | CHIP evaluation database |  | Once |  |
| By December 31, 2027, increase the number of CBOs that conduct standardized food security screening and referrals by 5 facilities. |  | To be determined December 31, 2026 |  | CHIP evaluation database |  | Quarterly |  |
| Long Term Outcome Indicator for Goals 3.1 |  | Baseline |  | NYSDOH Prevention Agenda Goal |  | Source |  |
| By December 31, 2030, increase food security among adults who make less than $25,000 by 5% from 78% to 81.9% |  | 78% (2024) |  | 51.1% (State-Level) |  | Orange County Community Health Survey |  |

| DOMAIN: SOCIAL & COMMUNITY CONTEXT |  |  |  |  |
| --- | --- | --- | --- | --- |
| PRIORITY AREA: ANXIETY AND STRESS |  |  |  |  |
| GOAL: Decrease anxiety and stress OBJECTIVE 5.1: By December 31, 2030, decrease the percentage of adults in households with an annual income of less than $25,000 who experience moderate or severe mental distress by 5% from 47% to 44%. (Data Source: Orange County Community Health Survey, 2024) DISPARITIES ADDRESSED: Individuals with low social-economic status (SES) |  |  |  |  |
| Evidence-Based Strategy | Lead Partners | Timeframe | Evaluation Measure | Outcome: Product/Result |
| Promote and increase awareness of evidence-based mindfulness resources to reduce the negative impact of stress and trauma | Staff Time: OCDOH, Montefiore St. Luke’s Cornwall Hospital Advisory Partners: OC CHIP Steering Committee, OC Dept of Mental Health, Changing the Ecosystem Taskforce, OASAS, Breath, Body, Mind Foundation, Wellness Inspiring Spiritual Health | September 1, 2026 through December 31, 2026 | # of staff trained through OASAS sponsored Breath, Body Mind Foundation # of outreach events attended to promote BBM # of participants trained | Increased number of residents with tools to reduce stress and anxiety |

| PERFORMANCE MEASURES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Short Term Process Indicators |  | Baseline | Source |  | Frequency |
| By December 2026, train at least one OCDOH Sr. Public Health Educator in the OASAS sponsored Breath, Body, Mind techniques. |  | Zero | CHIP evaluation database |  | Once |
| By December 2026, develop an outreach plan to identify outreach opportunities to work with the population of focus. |  | N/A | CHIP evaluation database |  | Once |
| By December 2027, provide at least 2 trainings to the population of focus. |  | Zero | CHIP evaluation database |  | Quarterly |
| PERFORMANCE MEASURES |  |  |  |  |  |
| Long Term Outcome Indicator | Baseline | NYSDOH Prevention Agenda Goal |  | Source | Frequency |
| Decrease the percentage of adults in households with an annual income of less than $25,000 who experience moderate or severe mental distress by 5% from 47% to 44%. | 47% (2024) | 18.9% by 2030 |  | Orange County Community Health Survey | Yearly |

| DOMAIN: HEALTHCARE ACCESS & QUALITY |  |  |  |  |
| --- | --- | --- | --- | --- |
| PRIORITY AREA: PREVENTATIVE SERVCIES FOR CHRONIC DISEASE PREVENTION AND CONTROL |  |  |  |  |
| GOAL: Increase Colorectal Cancer Screening OBJECTIVE 33.0: By December 31, 2030, increase the percentage of adults ages 45-75 who receive a colorectal cancer screening based on the most recent guidance by 5% from 75.1% to 78.8%. (Data source: NYS Behavioral Risk Factor Surveillance Survey, 2024) DISPARITIES ADDRESSED: Under-insured and uninsured individuals |  |  |  |  |
| Evidence-Based Strategy | Lead Partners | Timeframe | Evaluation Measure | Outcome: Product/Result |
| Work with the NYS Cancer Screening Program (CSP) to improve access to cancer screening and diagnostic testing for individuals who are under-insured or without health insurance | Staff Time: OCDOH, BSCH, Garnet Health, Montefiore St. Luke’s Cornwall Hospital, SACH, Orange County Cancer Collaborative, HITCH (CSP of the Hudson Valley), Cornerstone, OC Medical Reserves Corp Advisory, Support and Donation/Venue Partners: OC CHIP Steering Committee, American Cancer Society, Cultivating Health and Justice Initiative (CHJI), Insurance companies (Health First, Affinity by Molina), Touro Medical College, Hometown Healthcare | January 1, 2027 through December 31, 2030 | # of screening events # of individuals screened # of additional providers enrolled in CSP of the Hudson Valley | Increased number of adults able to receive colorectal cancer screenings |

| PERFORMANCE MEASURES |  |  |  |  |
| --- | --- | --- | --- | --- |
| Short Term Process Indicators for Goal 4.1 | Baseline |  | Source | Frequency |
| By December 2027, provide at least 3 screening events with opportunities to receive colorectal screenings or test kits. | Zero |  | CHIP Evaluation Database | Quarterly |
| By June 2028, increase the number of physicians enrolled in the CSP of the Hudson Valley program by 5. | To be determined |  | Provided by CSP of the Hudson Valley (HITCH) | Quarterly |
| By December 2027, increase the average number of attendees at screening events from 200 to 250. | 200 (3-year average 2024-YTD 2026) |  | CHIP Evaluation Database | Quarterly |
| Long Term Outcome Indicators for Goal 4.1 | Baseline | NYSDOH P.A. Goal | Source | Frequency |
| By December 31, 2030, increase the percentage of adults ages 45-75 who receive a colorectal cancer screening based on the most recent guidance by 5% from 75.1% to 78.8%. | 75.1% (2024) | 83.5% by 2030 | BRFSS | Every 4 years |